## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-05-b Puprize!
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | X | Initials: HAB, Date:10/19/22, Notes:
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. (DO NOT TEST)
Given that I am on the products page when there are products in the inventory then I see each product and short description.
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | X | Initials: KMC, Date:10/19/22, Notes:
As a buyer, I want to be able to see a categorized list of products so that I choose what to purchase. | Given that I do not input a specific search key/word when I choose to view the inventory then I expect to see the company's full inventory | X | Initials: HAB, Date:10/19/22, Notes:
Given that I input a specific search key/word when I choose to view the inventory then I expect to see a list of all items containing the keyword.
As an owner, I want to be able to change the order of visibility on newer/better products and information on my products so that I can increase revenue and make sure all the information is accurate on the products I am selling. | Given that I have an item that I want to prioritize when select this item in the inventory then I expect to see this item moved to the top of the display list that customers have access to. (DO NOT TEST) | X | Initials: HAB, Date:10/19/22, Notes:
Given that I no longer want to prioritize any items when I choose to reset the inventory then I expect to see the inventory returned to its default sorted order. (DO NOT TEST)
As an owner, I want to be able to update my stocks of products on my website so that my customers can buy more products and I only sell what I currently have available and not what's out of stock. | Given that I have products with 0 items currently in stock when I choose to update the inventory to reflect available items then I expect these products to be made unavailable for purchase. | X | Initials: HAB, Date:10/19/22, Notes:
Given that I add items to a product that was previously out of stock when I update the inventory then I expect to see these items made available for customers to purchase. (DO NOT TEST)
As a customer I want to add or remove items from my cart so I can purchase products I like for my dog. | Given that the shopping cart is empty when I select items from the products page then the items should appear in the shopping cart. | X | Initials: HAB, Date:10/19/22, Notes:
Given there are items in the shopping cart when I chose a product to be removed from the shopping cart then the product should not be in the shopping cart.
As a buyer, I want to be able to book appointments through the website so that I don't have to call or go in person to the salon. | Given that I want to book an appointment on a particular day when I select an available appointment slot on the appointment page then the appointment should be booked. | X | Initials: JBC, Date:10/19/22, Notes:
Given that I want to book an appointment when there are no appointments available then I should see a message saying there is no availability for this day. (DO NOT TEST)
As a Dog Owner, I want to be able to cancel appointments, so I don’t pay for a full appointment if something comes up. | Given that I have an appointment when I choose to cancel it then the appointment should be removed from my appointments (DO NOT TEST) | X | Initials: JBC, Date:10/19/22, Notes:
Given that I have an appointment when I choose to cancel it then the appointment will be made available again for other users. (DO NOT TEST)
As a Pet Groomer I want to see the appointment page so that I can update my personal schedule. | Given that I am a groomer when I check the appointments page then I expect to see the master calendar for appointments (HTTP STATUS: 200). (DO NOT TEST) | X | Initials: JBC, Date:10/19/22, Notes:
Given that I am a buyer when I check the appointments page then I expect to NOT see the master calendar for appointments (HTTP STATUS: 404).
As the Puprize! Owner I want to update the appointments list so that I can cancel an appointment for my groomers and set a new groomer for that appointment. | Given I am the owner and one of my groomer's has a schedule conflict when I change the groomer for an appointment then I expect the master calendar to be updated and the appointment be updated for the buyer (HTTP STATUS: 200). (DO NOT TEST) | X | Initials: JBC, Date:10/19/22, Notes:
Given that I am the owner and I want to close the salon for a given day when I block all appointments for that day then I expect that date to be unavailable for buyers to book appointments (HTTP STATUS: 200). (DO NOT TEST)
As a Dog Owner I want to create a pet profile so that the grooming experience is tailored towards the needs of my pet. | Given I have created a personal account when I decide to add a dog profile then I expect to be prompted with fields to create and save the dog profile (HTTP STATUS: 201). (DO NOT TEST) | N/A | Not implemented in this sprint.
As a Pet Owner I want to create my own profile so that all my information and pet profiles can be stored on one account to aid scheduling in the future. | Given I have created an account when I select an option to create my profile then I expect to see a template I can fill in and save. (DO NOT TEST) | X | Initials: RMR, Date: 10/19/22, Notes:
As a Pet Owner I want to update my pet profile(s) so that the grooming team can know the most current information of my pet's information. | Given that a pet profile exists when I select an option to edit then I expect the information in the page to be selectable and changable. (DO NOT TEST) | N/A | Not implemented in this sprint.
As a Customer I want to be able to request specific haircut so that my pet looks the way I want them to. | Given that I am creating an appointment when I select a haircut option then I expect the option to be saved and viewed by the groomer. (DO NOT TEST) | N/A | Not implemented in this sprint.
As a Pet Owner I want to see the FAQ page so that all my questions could possibly be answered. | Given I have questions about the salon when I go onto the FAQ page then the system should return a list of questions and answers and return a status code of 200 (DO NOT TEST) | N/A | Not implemented in this sprint.
As a Product Owner I want to update the FAQ so that I can add answers and change information to be recent and applicable. | Given the FAQ page is outdated, when I change the page, then the system should return an updated FAQ page with my changes and return a status code of 200 (OK) (DO NOT TEST) | N/A | Not implemented in this sprint.
Given I want to change the FAQ page, when I try to change something that does not exist or create a question/answer that already exists, then the system should return a status code of 404 (CONFLICT) (DO NOT TEST)
As a Business Owner I want to be able to easily provide information about required items (leash, collar, picture of style if specified) so that I can adequately handle the pets and provide a personalized experience for both the pet and for the customer. | Given I want to add information for the client on what to bring, when I change the text, then the system should update the text and return a status code of 200 (OK) (DO NOT TEST) | N/A | Not implemented in this sprint.
As a Owner of the estore I want to create my own login so that I can monitor my business and make changes to products. | Given I am prompted to login when I enter my owner-specific credentials then I expect to have access to owner-only actions. | X | Initials: RMR, Date: 10/19/22, Notes:
As a user I want to be able to see when I have put in an invalid input or when an error occurs so I know what went wrong and what to do. | Given that I have checked out when I have a cart of invalid products, then an error message should show. (DO NOT TEST) | N/A